## in
Phase | Category | Group | Sub-Group | Audit Type | Checklist Item | Importance | Mandatory | Implemented? (Yes / No) | Comments
Discovery | Business Objectives & KPIs | Business Objectives | Objectives | Manual | Define business objectives / success metrics (KPIs) and SEO / organic traffic goals | High | Yes | Yes | We have details about Business objecttives, Success metrics
Discovery | Business Objectives & KPIs | Business Objectives | Objectives | Manual | Document target audience and user personas | Medium | Yes | Yes
Discovery | Solution Architecture & System Context | CDN & Repository | Infrastructure | Manual | Identify CDN provider (Fastly, Cloudflare, Akamai, CloudFront); confirm GitHub repository setup and caching strategy | High | Yes | Yes
Discovery | EDS Requirements (Blocks, Routing/Page Model, Authoring Workflow, Content Sources, Query Index) | EDS Authoring & Content | Content | Manual | Define author roles, content sources (DA/UE), approval workflow, and preview requirements | High | Yes | Yes
Discovery | EDS Requirements (Blocks, Routing/Page Model, Authoring Workflow, Content Sources, Query Index) | EDS Block & Content Structure | Blocks | Manual | Identify required and custom blocks; define block performance requirements, variants, and content structure | High | Yes | Yes | Not applicable
Discovery | Integration & MarTech Requirements | Integration Requirements | Integrations | Manual | Define all integration requirements: analytics tool, API authentication standards, CRM, commerce engine, A/B testing, and MarTech | High | Yes | NA | Still we are in component development phase e Phase 1. In phase 2 we have analytics
Discovery | Non-Functional Requirements (Performance, Security, Accessibility) | Non-Functional Requirements | NFRs | Manual | Define NFRs: Lighthouse 100 performance target, WCAG conformance level, security / compliance, scalability, availability, and browser / device support | High | Yes | Yes | But lighthouse score we are targetting above 80, Accessibility is AA
Discovery | SEO, Analytics & Consent Requirements | Routing & Localization | Routing | Manual | Define URL structure, routing patterns, redirect requirements, sitemap, localization workflow, and canonical URL hierarchy | High | Yes | Yes
Design | High-Level / Low-Level Design (HLD/LLD) | High-Level Design (HLD) | HLD | Manual | Document HLD: No framework, build-less delivery, no SPA assumptions, navigation and global layout strategy | High | Yes | Yes
Design | EDS Architecture Design (Blocks/Fragments/SSG) | Block & Fragment Design | Blocks | Manual | Design block structure, loading strategy (eager vs lazy), decoration patterns, and fragment organization and naming conventions | High | Yes | Yes | But this is not an EDS, however we are dynamically loading JS and CSS on demand (if component is present on the page)
Design | Performance-by-Design (CWV, Lighthouse) | Performance Design | Performance | Manual | Define performance goals: Core Web Vitals targets (LCP / CLS / TTFB), critical CSS strategy, image optimization, and above-the-fold priority | High | Yes | Yes
Design | Reusability & Component Strategy | Responsive & Accessibility Design | Responsive | Manual | Define responsive strategy and breakpoints, ARIA usage philosophy, third-party script isolation, analytics excluded from critical rendering, and accessibility considered at architecture level | High | Yes | Yes
Design | Technical SEO Design (URL, metadata, schema) | SEO & Error Strategy | SEO | Manual | Design metadata / SEO strategy (OpenGraph, Schema.org), define error page strategy, and align URL structure with SEO | High | Yes | Yes | These are defined and some of them are implemented like error pages, url's. Currently we are still development the component, once done these changes will be picked up
Setup | CDN & Caching Setup | CDN Setup | CDN | Manual | Configure CDN: provider, caching rules, SSL / TLS certificates, push invalidation for instant cache purge, and custom HTTP headers | High | Yes | Yes
Setup | Environment & Repo Setup | Repository & Content Source | Repository | Manual | Set up GitHub repository with EDS boilerplate, configure fstab.yaml content source mapping, branch protection, and repository settings | High | Yes | Yes
Setup | EDS Config (Sidekick, Content Source, Repo, Config) | AEM Sidekick & Content Folder | Sidekick | Manual | Install AEM Sidekick for team; create and share content folder with Adobe (helix@adobe.com); configure Sidekick-to-repository connection and folder permissions | High | Yes | Yes | As this is a AEM sites, so we have storybook setup
Setup | CI/CD Pipeline & PR Process | CI/CD Pipeline | CI/CD | Manual | Set up CI/CD pipeline with automated quality checks (Lighthouse, accessibility), build triggers, deployment automation, and pre-commit hooks (lint + unit tests) | High | Yes | Yes | Lighthouse is not integrated with CI/CD pipeline and rest are implemented
Setup | Environment & Repo Setup | Environment Setup | Environments | Manual | Set up dev / staging / production environments with parity; establish staging and preview environments; document environment configuration and access; verify Design Token Adherence | High | Yes | Yes
Setup | CI/CD Pipeline & PR Process | PR Process & Standards | Process | Manual | Define branching strategy; enforce mandatory PR review on main; author merges own PR after approval; aem.js unchanged; establish code review standards | High | Yes | Yes
Setup | Translation / i18n Setup | Library & Translation Setup | Libraries | Manual | Prefer vanilla JS; define and document approved libraries with justification; configure multi-language support, placeholders management, and locale routing if required | Medium | Yes | Yes
Visual Design | Design Handoff & QA | Design Fidelity | Fidelity | Manual | UI layout matches approved design mockups / Figma at all viewports; spacing, padding, alignment, and typography match design specifications within acceptable tolerance | High | Yes | Yes
Visual Design | Branding & Design Tokens | Brand & Interactive States | Brand | Manual | Interactive element states (hover, active, disabled, selected) are visually distinct and consistent; brand colors, imagery, and icon style are applied consistently throughout | High | Yes | Yes
User Experience | User Journeys & Flows | Navigation & User Flows | Navigation | Manual | Core user flows (signup, login, purchase, search) are intuitive and require minimal steps; multi-step processes show clear progress indication; destructive actions require explicit confirmation | High | Yes | Yes
User Experience | Interaction Design (States, Errors) | Feedback & States | States | Manual | Loading states, empty states, and error recovery paths provide meaningful visual feedback; success and failure messaging is timely and visible without requiring scroll | High | Yes | Yes
User Experience | Forms & Validation UX | Forms & Input | Forms | Manual | Form validation messaging is clear and specific; field tab order matches visual layout; inline validation timing is appropriate; auto-fill and password manager compatibility verified | High | Yes | Yes
Content Quality | Legal/Compliance Review | Copy & Legal | Copy | Manual | Content is free of spelling and grammatical errors; microcopy (button labels, tooltips, placeholders) is clear and consistent in tone; legal text (ToS, privacy policy, disclaimers) is present and linked from all pages | High | Yes | Yes
Content Quality | Legal/Compliance Review | Compliance & Cookie Consent | Compliance | Manual | Cookie consent banner meets GDPR / CCPA / ePrivacy requirements; consent choices are respected across sessions; user data handling complies with applicable privacy regulations | Critical | Yes | Yes | These changes will be implemented in phase 2
Testing | Integration & E2E Testing | Content & Publish Workflow | Publishing | Manual | Validate content preview shows 100% production fidelity; test one-click publish; validate instant cache purge after publishing; test content updates and republishing | High | Yes | NA | This is not an EDS project
Testing | Integration & E2E Testing | Functional & Integration | Functional | Manual | Test all custom blocks, interactive features, forms, end-to-end user journeys, error scenarios, and third-party API integrations | High | Yes | Yes | This is done wrt AEM sites
Testing | Unit Testing | Unit Testing | Unit Tests | Manual | Write and automate unit tests for custom JavaScript functions and blocks in CI/CD; test utility functions; mock external dependencies; verify manual business logic test cases | High | Yes | No | This is not in requirement. Currently we are doing manual unit testing from developer and handed over to QA
Testing | SEO / Analytics Validation | RUM Setup | Monitoring | Manual | Set up and configure RUM (Real User Monitoring) tracking and data collection | High | Yes | NA | This will be implemented in phase 2 as we will work on analytics later
Testing | Cross-browser / Device Testing | Visual & Cross-Browser | Visual | Manual | Perform visual regression testing across browsers (Chrome, Firefox, Safari, Edge) and devices (mobile, tablet, desktop); validate responsive design at all breakpoints; test dark mode / theme variations | High | Yes | Yes
Security | API Security | API & Input Security | API | Manual | Secure all API endpoints: authentication, input sanitization, rate limiting, CORS policies, and API versioning strategy | High | Yes | Yes
Security | Security Standards | Access Control | Access | Manual | Implement RBAC; verify content folder and GitHub access controls; conduct regular access reviews and audits | High | Yes | Yes
Security | Security Standards | Data Protection | Data | Manual | Implement data encryption at rest and in transit; implement GDPR compliance; configure privacy settings and cookie consent; document data handling policies | High | Yes | Yes
Security | Secrets Management | Secrets & Vulnerability Management | Secrets | Manual | Use environment variables for sensitive config; implement key rotation; use secret management tools; review security audit findings; test for common web vulnerabilities (XSS / CSRF); conduct penetration testing | High | Yes | Yes
Author Validation | Author Training & Enablement | Author Training & Sidekick | Training | Manual | Verify AEM Sidekick installation and functionality; provide author training documentation; conduct hands-on training sessions | High | Yes | Yes | This not EDS, but we have documents for author wrt AEM site
Author Validation | Author Workflow Validation | Author Workflow Validation | Workflow | Manual | Validate authors can create content in Word / Google Docs and Excel / Sheets; verify content approval workflow; test content versioning and revision history | High | Yes | Yes
Author Validation | Block Usability Review | Block Usability Review | Blocks | Manual | Ensure blocks are intuitive for authors; validate block configuration options are clear; create block usage documentation for authors | High | Yes | Yes
Author Validation | Document-to-Web Rendering Validation | Rendering & Publishing | Publishing | Manual | Verify document-to-web rendering (formatting, tables, images); test fragment embedding and update propagation; test one-click publish, cache purge, preview fidelity, and bulk metadata updates | High | Yes | Yes
Performance | Caching / CDN Validation | Caching Strategy | Caching | Manual | Leverage CDN caching with instant purge; configure appropriate cache headers; test cache invalidation strategies; implement effective browser caching | High | Yes | Yes
Performance | Performance Monitoring (RUM/Synthetic) | RUM & Monitoring | Monitoring | Manual | Monitor RUM data for performance insights; set up performance degradation alerts; track performance trends over time | High | Yes | Yes
Performance | Core Web Vitals (CWV) Metrics | Perceived Performance | Perceived | Manual | Above-the-fold content loads within 2.5s on representative network conditions; scroll performance is smooth with no jank; third-party script failures do not block or degrade core page functionality | High | Yes | Yes
Accessibility | Screen Reader Testing | Screen Reader & WCAG | WCAG Core | Manual | Test with screen readers (NVDA, JAWS, VoiceOver); verify WCAG 2.1 Level AA compliance; validate color and sensory characteristics are not the sole means of conveying information | High | Yes | Yes
Accessibility | Keyboard Navigation | Keyboard Navigation | Keyboard | Manual | Test keyboard-only navigation (Tab, Shift+Tab, Enter / Space, Arrow keys); ensure all interactive elements are keyboard accessible with visible focus indicators | High | Yes | Yes
Accessibility | WCAG 2.1 AA Compliance | Accessibility Tools & Media | Tools | Manual | Run axe / WAVE tools and address all flagged issues; verify captions / transcripts for video and audio content; validate skip links and provide clear error messages; test at 400% zoom | High | Yes | Yes
Internationalization | RTL / BiDi Support | Localization & RTL | RTL | Manual | RTL layout renders correctly with mirrored icons and directional elements; text expansion (up to 200%) does not break layouts or cause overflow; locale-specific formatting (date, time, currency, numbers) is correct for target markets | High | Yes | Yes
Architecture & Code Review | Architecture Review & ADRs | Design System & Tokens | Tokens | Manual | Design system tokens in code match latest design specifications (no drift from Figma); component library documentation is complete and includes usage examples for all variants | High | Yes | Yes
Architecture & Code Review | Tech Debt & Documentation | Build & Font Strategy | Fonts | Manual | Webfont loading strategy reviewed to prevent FOIT / FOUT in production; third-party library choices are justified with no redundant libraries serving the same purpose | High | Yes | Yes
Pre-GoLive | Caching Rules Finalization | Caching & DNS Finalization | DNS | Manual | Finalize CDN caching configuration, validate cache TTL settings, configure push invalidation; configure DNS records, SSL / TLS certificates, plan DNS cutover, and test DNS propagation | High | Yes | Yes
Pre-GoLive | Deployment & Cutover Plan | Deployment & Rollback Plan | Deployment | Manual | Create deployment runbook; define schedule and maintenance window; assign roles and responsibilities; prepare and test rollback plan; define rollback decision criteria | High | Yes | Yes
Pre-GoLive | DNS & Domain Validation (Preview/Live) | Domain Validation | Domain | Manual | Validate preview and live domain configuration; verify custom domain mapping; test preview-to-live promotion workflow | High | Yes | Yes
Pre-GoLive | Rollback Plan & Dry Run | Final Testing | Testing | Manual | Complete E2E testing, smoke testing, and load testing in production-like environment; validate all integrations in production | High | Yes | Yes
Pre-GoLive | SEO Launch Checklist (robots/sitemap/canonicals) | SEO & Go-Live Readiness | SEO | Manual | Validate all URL redirects (301/302) and test redirect chains; submit sitemap; configure robots.txt; verify metadata; set up Google Search Console; enable RUM; finalize technical documentation and author guidelines | High | Yes | Yes
Post-GoLive | Error Tracking & Logging | Logging & Alerts | Alerts | Manual | Configure centralized logging; set up error rate, uptime, performance threshold, and security event alerts | High | Yes | Yes
Post-GoLive | Monitoring/Alerts & Incident Response | Monitoring Setup | Monitoring | Manual | Monitor Core Web Vitals, RUM metrics, CDN performance and cache hit rates, traffic patterns, and peak loads | High | Yes | Yes
Post-GoLive | Author Support Process | Author Support | Support | Manual | Provide ongoing author support; establish helpdesk channel; create FAQ and troubleshooting guides; gather author feedback | Medium | Yes | Yes
Post-GoLive | Hypercare & Production Support | Production Support | Production | Manual | Establish incident response procedures; define SLA for issue resolution; create support documentation and runbooks; set up support ticketing system | High | Yes | Yes
Post-GoLive | SEO Monitoring & Index Health | SEO & Analytics | Analytics | Manual | Monitor search engine indexing status; track business KPIs and organic traffic; review site analytics and user behavior | Medium | Yes | Yes
Post-GoLive | Backlog Triage & Continuous Improvement | Continuous Improvement | Improvement | Manual | Conduct regular performance audits; review Adobe automated performance PRs; keep dependencies updated; implement improvement suggestions based on user feedback | Medium | Yes | Yes
Process & Governance | SDLC / Ways of Working | Project Management | Project | Manual | Project management tool actively used (Jira / Azure DevOps / Linear); all work tracked with tickets, acceptance criteria, and Definition of Done; bug tickets include reproduction steps and severity | High | Yes | Yes
Process & Governance | Quality Gates & Acceptance Criteria | Code Review Process | Code Review | Manual | Code review process defined with SLA (e.g. 24h turnaround); reviewers check functionality, readability, security, performance, and accessibility; feedback is constructive and references standards | High | Yes | Yes
Process & Governance | Quality Gates & Acceptance Criteria | QA & Release | QA | Manual | QA environment mirrors production; regression tests executed before each release; cross-browser / device test matrix defined; UAT / stakeholder sign-off required before production deployment | High | Yes | Yes
Process & Governance | Compliance & Audit Trail | GenAI Governance | GenAI | Manual | GenAI usage policy documented and communicated to all team members; approved tools list maintained; proprietary code and customer data not submitted to public AI services; enterprise licensing verified | Critical | Yes | Yes